## Test-Plan History
Version | Data | Author | Update
0.1 | 17.03.2020 | Rudenko Vladyslav & Sergii Glivinskiy | Initial Version
0.5 | 10.09.2020 | Rudenko Vladyslav & Sergii Glivinskiy | Added Security Roles
0.8 | 23.01.2021 | Rudenko Vladyslav & Sergii Glivinskiy | Added Filters
0.9 | 29.10.2021 | Rudenko Vladyslav & Sergii Glivinskiy | Added "Order status" subtab to the Report tab
1.0 | 16.01.2022 | Rudenko Vladyslav & Sergii Glivinskiy | Final Version

## Strategy
Item | Description
Project Overview | System A functionality within this sprint
Introduction | System A is the client’s system that stores data about customers and their purchase history System A can be accessed with two types of security permission: 1. Security Role X 2. Security Role Y The Software has 2 tabs and individual subtabs accordingly: 1. Filter: + Period (for both Client and Product) + Start Date + End Date 2. Report: + Client + Order Date + Ordered Products + Order Status
Testing Overview | Please go to the "Test Approach" sheet
Test Cases | Test-Cases format: .xlsx
Defect Management | To work with defects, it is expected to use such documentary media as: .xlsx JIRA
Change Management | Changes and improvements should follow the following process: + Changes/improvements must be visibly documented by the Project Manager/Business Analyst and if required, a new User Story must be created or a version of an existing User Story must be modified + Change must be reviewed and accepted/rejected by Project Sponsor (Customer or End User) + The change is submitted to the technicians via a User Story document + As soon as the User Story is approved (signed off) by all interested parties, Developers and Testers begin their activities related to these changes + Test documentation is being created + The schedule is being revised to reflect changes or a new work schedule/schedule is being created
Suspension Criteria | The testing process is suspended by the decision of Development Manager / Project Manager / Test Manager in case of finding strict / blocking defects
Resumption Criteria | Resuming includes retesting functionality and defects to make sure the functionality works as expected before moving on to the next phase of testing.
Entry Criteria | + Unit/Unit Integration tests are prepared for this sprint and the application is ready for testing [Development Manager] + User Stories, Test Сases were created and approved [Business Analyst] + If tools like JIRA are going to be used, they must be configured, given the appropriate user rights for them, and they must be ready to use [Test Manager] + There was approval to run System Functional testing by Alex [Team Lead] + No outstanding known Severe or High-level defects
Exit Criteria | + All In-Scope testing has been completed + No unresolved known Severe or High-level defects + All found defects are documented and fixed + Management and Development has agreed the unresolved Medium or Low-level defects are acceptable impact + The testing process is suspended by the decision of Development Manager / Project Manager / Test Manager in case of finding strict / blocking defects + Successful completion of the test phase in the form of a Test Summary Report, which is approved by the Project Manager
In Scope | Focus on Security, UI, UX: + GUI testing of system control + Access to the system using 2 types of security permission: Security Role X/Y + Filter working (sorting by Start/ End Date) + Report availability only for Users with security role Y
Out-Of-Scope | + Stress testing of report availability for Users with security role Y
Risks | + Staff absence may cause delays on any solution [Project management] + Short deadlines/ timing + Internet/ electricity-access problems + Different time zones of the team members
Timescales | Expected testing estimates: + Test planning – 2 days + Requirements analysis – 1 day + Test scripting and preparation – 6 days + Execute scripts and repeat testing – 7 days + Test completion report – 1 day
Test Environment | Approved Devices/ OS/ Versions: + Windows 7, 8, 10 ¦ 64bit + Linux Ubuntu + MacOS + Android 8.0.0+ + IOS 12.0.2+
People/ Team | + Project Management – Sergii Glivinskiy + Business Analysts – Levi Olsen + Senior Tester – Natalia Bondarets + Developer – Qui Hoang + Junior QA – Vladyslav Rudenko

## Work Schedule
February
Function | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Report creation
Security Permission Access
Filter working
Report availability only for Users with security role Y
Legend
In Progress
ready to be tested
Test planning and preparing
In Testing
Successfully tested

## Stakeholders
Stakeholders on the project
Name | Role
Sergei Glivinskiy | Dev Manager
Popov Roman | Test Manager
Sergey Kurioza | Business analyst
Roman Vasyta | Tech Lead
Rudenko Vladyslav | Junior QA Engineer

## Links
№ | Source | Author
1 | Jira link https://www.atlassian.com/ru/software/jira | Dev Team
2 | GitHub: https://github.com/VladRudenko | Vladyslav Rudenko